## Read 1st
CCDM programme plan
There are five tabs in this workbook:
1. Overall plan (master plan for implementing CCDM in all wards)
2. Annual plan (for the current year)
3. Detailed workplan (is a duplicaiton of the road map for each component)
4. Monthly status report (against the detialed workplan)
5. Quarterly report (against the annual plan)
This CCDM workbook is designed to help you:
1. Plan and document the overall and annual CCDM plan
2. Identify who needs to do what when on the detailed workplan
3. Complete monthly status reporting by using a consistent strucutured template
4. Compete quarterly reporting to the SSHW Unit Governance Group
Each of the worksheets have instructions at the beinning to help you with - what, who, how and when. These instructions are for your reference only the rows can be hidden while you are working in the document.

## 1. Overall plan
CCDM overall implementation plan | [6 empty] | Last Updated: |  |  | By:
What | This worksheet is a template for documenting the master plan for implementing CCDM in all wards.
Who | The SSHW Programme Consultant completes worksheet in collaboration with the CCDM Site Coordinator and Co-chairs.
How | Complete the table below using the key colour and associated abbreviation for the work e.g. TrendCare = TC (see more abbreviations below)
Use these documents for planning - CCDM programme standards, road maps, FTE for programme implementation.
Document the hospital-wide plan for TrendCare (TC), CCDM governance (Council, LDC), core data set (CDS) and variance response management (VRM).
Document the plan for implementing local data councils, core data set, staffing methodology and VRM for each ward/unit.
Consider sequencing that is needed i.e. some things need to come before others e.g. TrendCare upgrades before FTE calculations, resource to respond before variance response management etc.
Factor in time to establish standard operating procedures for business as usual.
Review the 'FTE req.' tab to establish the resource implications. Adjust scheduling as needed.
Discuss the draft with Co-chairs. Submit to CCDM council for endorsement
When | Complete at the beginning of programme implementation. Review and update at least annually.
|  |  |  | Key: |  |  |  |  | BAU | On hold | No TrendCare
[5 empty] | Planned | In progress | Completed | Not done | Business as usual
[5 empty] | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4
DHB wide/Hospital site | Directorate | Ward name | Standard | Key milestone | Jul-18 | Oct-18 | Jan-19 | Apr-19 | Jul-19 | Oct-19 | Jan-20 | Apr-20 | Jul-20 | Oct-20 | Jan-21 | Apr-21 | Jul-21 | Oct-21 | Jan-22 | Apr-22
DHB | N/A | N/A | 1. Governance | CCDM council established | Council
DHB | N/A | N/A | 2. Patient acuity tool | TrendCare data accurate |  |  |  |  | TC | TC | TC | TC
DHB | N/A | N/A | 3. Core data set | Core data set implemented | [6 empty] | CDS | CDS | CDS
DHB | N/A | N/A | 4. Staffing methodology | FTE calculations completed | [10 empty] | FTE | FTE
DHB | N/A | N/A | 5. Variance response management | Variance response management in use | [11 empty] | VRM | VRM | VRM | VRM
Site 1 | Medical | Ward 1 | 1. Governance | Local council established | [5 empty] | LDC
Site 1 | Medical | Ward 1 | 2. Patient acuity tool | TrendCare data accurate
Site 1 | Medical | Ward 1 | 3. Core data set | Core data set implemented
Site 1 | Medical | Ward 1 | 4. Staffing methodology | FTE calculation completed
Site 1 | Medical | Ward 1 | 5. Variance response management | Variance response management in use | [13 empty] | P
Site 2 | Medical | Ward 20 | 1. Governance | Local council established
Site 2 | Medical | Ward 20 | 2. Patient acuity tool | TrendCare data accurate
Site 2 | Medical | Ward 20 | 3. Core data set | Core data set implemented
Site 2 | Medical | Ward 20 | 4. Staffing methodology | FTE calculation completed
Site 2 | Medical | Ward 20 | 5. Variance response management | Variance response management in use

## 2. Annual plan 20YY-20YY
CCDM Programme Annual Plan |  |  | Last Updated: | By:
What | This worksheet is a template for documenting the annual plan for implementing CCDM. It is taken from the master plan.
Who | The SSHW Programme Consultant completes worksheet in collaboration with the CCDM Site Coordinator and Co-chairs.
How | Rename worksheet Annual plan 20YY-20YY. For subsequent years create a new worksheet.
Complete the table below using the key colour and text.
Take the selected year from the Overall plan and document it in more detail below.
Use these documents for planning - CCDM programme standards, road maps, FTE for programme implementation.
Hide inactive rows i.e. rows where there is no activity in the current year.
Consider sequencing i.e. some things needs to come before others e.g. TrendCare upgrades and FTE calculations, variance response management when there is no long term plan to respond etc.
Factor in time to establish standard operating procedures for business as usual.
Check the 'FTE req.' tab to establish the resource implications. Adjust scheduling as needed.
Discuss the draft with Co-chairs. Submit to CCDM council for endorsement.
Report on progress against the plan to CCDM council/working group as required.
When | Complete as per the road map. This is a live document. Update progress against plan at least monthly.
|  |  | Key: | P | IP | C | <30 | 30-60 | >60
|  |  |  | Planned | In progress | Completed | Less than 30 days over | 30-60 days over | greater than 60 days over
Standard | No. | Main steps | Resource required | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
1. Governance | 1 | Set up CCDM council | bar: Jul to Dec
1. Governance | 2 | Review partnership for the council | bar: Aug; Jan to Mar
1. Governance | 3 | Complete workshops for the council
1. Governance | 4 | Complete standards assessment
1. Governance | 5 | Write & agree workplans
1. Governance | 6 | Establish working groups as per overall plan
1. Governance | 7 | Monitor & report against workplan/s
1. Governance | 8 | Establish XX local data councils
2. Validate patient acuity tool | 10 | bar: Jul to Aug
2. Validate patient acuity tool | 11 | bar: Nov
2. Validate patient acuity tool | 12
2. Validate patient acuity tool | 13
2. Validate patient acuity tool | 14
2. Validate patient acuity tool | 15
2. Validate patient acuity tool | 16
2. Validate patient acuity tool | 17
2. Validate patient acuity tool | 18
2. Validate patient acuity tool | 19
3. Core data set | 20 | Set up working group | bar: Apr to May
3. Core data set | 21 | Complete workshops
3. Core data set | 22 | Complete stocktake
3. Core data set | 23 | Agree roll out plan
3. Core data set | 24 | Write & agree detailed workplan
3. Core data set | 25 | Agree & document process for business as usual
3. Core data set | 26 | Establish layout & start date
3. Core data set | 27 | Review , report & improve measures
4. FTE calculation | 30 | Set up working group
4. FTE calculation | 31 | Complete workshops
4. FTE calculation | 32 | Complete stocktake
4. FTE calculation | 33 | Write & agree detailed workplan
4. FTE calculation | 34 | Collect & collate data inputs xx wards
4. FTE calculation | 35 | Agree data inputs xx wards
4. FTE calculation | 36 | Enter data into software xx wards
4. FTE calculation | 37 | Complete roster testing xx wards
4. FTE calculation | 38 | Draft report & agree recommendations xx wards
4. FTE calculation | 39 | Implement FTE & roster xx wards
4. FTE calculation | 40 | Monitor variance to roster & budget xx wards
5. Variance response management | 42
5. Variance response management | 43
5. Variance response management | 44
5. Variance response management | 45
5. Variance response management | 46
5. Variance response management | 47
5. Variance response management | 48
5. Variance response management | 49
5. Variance response management | 50
5. Variance response management | 51

## 3. Detailed workplan
CCDM detailed workplan |  | Last updated: | By:
What | This worksheet is a template for documenting the weekly plan for implementing CCDM. It is taken from the annual plan.
The detailed workplan is a key project management tool.
Who | The SSHW Programme Consultant completes plan in collaboration with the CCDM Site Coordinator. The Coordinator maintains the live document.
How | Rename worksheet tab 'Detailed workplan xx directorate/service/ward'. Create a new worksheet for each.
Complete the table below using the key colour and text.
Take the Annual plan and document it in more detail below. If needed, use a printed road map for visual re-inforcement of the process.
Hide inactive rows i.e. rows where there is no activity in the current year.
Use the detailed plan to populate the monthly status report.
When | Review and update the status weekly.
|  |  | Key: | P | IP | C | <30 | 30-60 | >60
|  |  |  | Planned | In progress | Completed | Less than 30 days over | 30-60 days over | greater than 60 days over
Week
Component | Main steps | Actions | By who | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
CCDM governance | Main steps | Actions | By who
CCDM governance | Set up CCDM council & review partnership | Present the CCDM programme overview (PPP) | Programme Consultant
CCDM governance | Set up CCDM council & review partnership | Guide discussion on CCDM council terms of reference | Programme Consultant
CCDM governance | Set up CCDM council & review partnership | Guide discussion on workshops outline | Programme Consultant
CCDM governance | Set up CCDM council & review partnership | Agree CCDM council members & terms of reference | CCDM council
CCDM governance | Set up CCDM council & review partnership | Present What is CCDM governance (PPP) | Programme Consultant
CCDM governance | Set up CCDM council & review partnership | Set up regular CCDM council meetings | CCDM council
CCDM governance | Set up CCDM council & review partnership | Coordinate partnership evaluation | CCDM Site Coordinator Programme Consultant
CCDM governance | Set up CCDM council & review partnership | Guide discussion on the partnership evaluation tool | Programme Consultant
CCDM governance | Set up CCDM council & review partnership | Complete partnership evaluation | Local data council Working groups CCDM council
CCDM governance | Set up CCDM council & review partnership | Collate results and make recommendations | CCDM Site Coordinator Programme Consultant
CCDM governance | Set up CCDM council & review partnership | Review recommendations, agree decisions and communicate to staff | CCDM council
CCDM governance | Complete workshops & standards assessment | Plan workshops | CCDM Site Coordinator Programme Consultant
CCDM governance | Complete workshops & standards assessment | Guide discussion on CCDM programme standards | Programme Consultant
CCDM governance | Complete workshops & standards assessment | Guide discussion on CCDM programme overall, annual and detailed workplan & reporting template | Programme Consultant
CCDM governance | Complete workshops & standards assessment | Present on How the programme uses TrendCare data (PPP) | Programme Consultant
CCDM governance | Complete workshops & standards assessment | Attend workshops on tools & processes, as needed | Local data council Working groups CCDM council
CCDM governance | Complete workshops & standards assessment | Coordinate standards assessment | CCDM Site Coordinator Programme Consultant
CCDM governance | Complete workshops & standards assessment | Review results of standards assessment | CCDM council
CCDM governance | Write & agree workplans, establish working groups | Guide discussion on Preparing the overall & annual plan | Programme Consultant
CCDM governance | Write & agree workplans, establish working groups | Draft/revise the overall and annual workplan | CCDM Site Coordinator Programme Consultant
CCDM governance | Write & agree workplans, establish working groups | Endorse overall & annual workplans | CCDM council
CCDM governance | Write & agree workplans, establish working groups | Communicate overall & annual workplans with staff | CCDM council
CCDM governance | Write & agree workplans, establish working groups | Send overall & annual plan to SSHW Unit Governance Group | CCDM council
CCDM governance | Write & agree workplans, establish working groups | Agree structure for working groups | CCDM council
CCDM governance | Write & agree workplans, establish working groups | Set up regular working group meetings | CCDM council
CCDM governance | Write & agree workplans, establish working groups | Attend working group | Working group
CCDM governance | Monitor & report against workplans | Guide discussion on Preparing the status report | Programme Consultant
CCDM governance | Monitor & report against workplans | Draft monthly status report | CCDM Site Coordinator Programme Consultant
CCDM governance | Monitor & report against workplans | Monitor progress (monthly) | CCDM council
CCDM governance | Monitor & report against workplans | Guide discussion on preparing the quarterly report | Programme Consultant
CCDM governance | Monitor & report against workplans | Prepare quarterly report | CCDM Site Coordinator Programme Consultant
CCDM governance | Monitor & report against workplans | Endorse quarterly report | CCDM council
CCDM governance | Monitor & report against workplans | Communicate quarterly report to staff | CCDM council
CCDM governance | Monitor & report against workplans | Send quarterly report to SSHW Unit Governance Group | CCDM council
CCDM governance | Monitor & report against workplans | Review meeting process (annually) | CCDM council
CCDM governance | Monitor & report against workplans | Coordinate annual standards assessments as business as usual | CCDM Site Coordinator Programme Consultant
CCDM governance | Monitor & report against workplans | Monitor core data set as business as usual | CCDM council
CCDM governance | Establish local data councils | Guide discussion on local data council terms of reference | Programme Consultant
CCDM governance | Establish local data councils | Set up permanent local data council | Local data council
CCDM governance | Establish local data councils | Present on What is a local data council | Programme Consultant
CCDM governance | Establish local data councils | Attend workshops on tools & processes | Local data council
CCDM governance | Establish local data councils | Share communications | Local data council
CCDM governance | Establish local data councils | Monitor core data set as business as usual | Local data council
CCDM governance | Establish local data councils | Report on core data set as business as usual | Local data council
Core data set | Main steps | Actions | By who
Core data set | Set up working group & workshops | Agree working group members & TOR | CCDM council
Core data set | Set up working group & workshops | Set up regular working group meetings | CCDM Site Coordinator Programme Consultant
Core data set | Set up working group & workshops | Guide discussion on planning workshops | CCDM Site Coordinator Programme Consultant
Core data set | Set up working group & workshops | Plan workshops | Working group
Core data set | Set up working group & workshops | Present core data set introduction (PPP) | Programme Consultant
Core data set | Set up working group & workshops | Guide discussion on core data set dictionary | CCDM Site Coordinator Programme Consultant
Core data set | Set up working group & workshops | Guide discussion on working group TOR | CCDM Site Coordinator Programme Consultant
Core data set | Set up working group & workshops | Guide discussion on core data set specifications | CCDM Site Coordinator Programme Consultant
Core data set | Complete stocktake & agree roll out plan | Initiate stocktake | Working group
Core data set | Complete stocktake & agree roll out plan | Guide discussion on core data set stocktake for business as usual | CCDM Site Coordinator Programme Consultant
Core data set | Complete stocktake & agree roll out plan | Coordinate information gathering of the stocktake | CCDM Site Coordinator Programme Consultant
Core data set | Complete stocktake & agree roll out plan | Guide discussion on options for implementation | CCDM Site Coordinator Programme Consultant
Core data set | Complete stocktake & agree roll out plan | Review stocktake findings & agree options for implementation | Working group
Core data set | Complete stocktake & agree roll out plan | Agree the strategy for overall roll out | Working group
Core data set | Complete stocktake & agree roll out plan | Endorse & communicate roll out sequence | CCDM council
Core data set | Complete stocktake & agree roll out plan | Communicate strategy for overall roll out | CCDM council
Core data set | Complete stocktake & agree roll out plan | Present What is a local data council (PPP) | CCDM Site Coordinator Programme Consultant
Core data set | Complete stocktake & agree roll out plan | Set up permanent local/directorate data council | Clinical manager / Ward / Directorate
Core data set | Write & agree detailed workplan | Guide discussion on the detailed workplan | CCDM Site Coordinator Programme Consultant
Core data set | Write & agree detailed workplan | Draft detailed workplan | CCDM Site Coordinator Programme Consultant
Core data set | Write & agree detailed workplan | Agree detailed workplan & report monthly | Working group
Core data set | Write & agree detailed workplan | Monitor progress against detailed workplan | CCDM council
Core data set | Write & agree detailed workplan | Go over the workplan with the local/directorate data council as per plan | Clinical manager / Ward / Directorate
Core data set | Agree & document process for business as usual | Guide discussion on process for business as usual | CCDM Site Coordinator Programme Consultant
Core data set | Agree & document process for business as usual | Draft process for business as usual | CCDM Site Coordinator Programme Consultant
Core data set | Agree & document process for business as usual | Agree process & draft staff communications | Working group
Core data set | Agree & document process for business as usual | Endorse & communicate process | CCDM council
Core data set | Agree & document process for business as usual | Go over local/directorate data council process | Clinical manager / Ward / Directorate
Core data set | Agree & document process for business as usual | Present on core data set for local data council | CCDM Site Coordinator Programme Consultant
Core data set | Establish layout & start date | Guide discussion on core data set specifications | CCDM Site Coordinator Programme Consultant
Core data set | Establish layout & start date | Prepare layout options (LDC, ward, directorate, hospital view) | CCDM Site Coordinator Programme Consultant
Core data set | Establish layout & start date | Review and make recommendations on layout | Working group
Core data set | Establish layout & start date | Endorse & communicate layouts | CCDM council
Core data set | Establish layout & start date | Communicate layout | CCDM council
Core data set | Establish layout & start date | Authorise commencement of data collection/monthly reporting | CCDM council
Core data set | Establish layout & start date | Notify groups/meetings (where core data set to be reviewed) of start date | Working group
Core data set | Review, report & improve measures | Work with groups/meetings to establish core data set. Review as business as usual | CCDM Site Coordinator Programme Consultant
Core data set | Review, report & improve measures | Present Using your data set (PPP) | CCDM Site Coordinator Programme Consultant
Core data set | Review, report & improve measures | Review core data set measures monthly | Clinical manager / Ward / Directorate
Core data set | Review, report & improve measures | Present / guide discussion on improvement & reporting template | CCDM Site Coordinator Programme Consultant
Core data set | Review, report & improve measures | Develop/review improvement template | Clinical manager / Ward / Directorate
Core data set | Review, report & improve measures | Report progress on reporting template & status report | Clinical manager / Ward / Directorate
Core data set | Review, report & improve measures | Change measures that need to be improved, as needed | Clinical manager / Ward / Directorate
Core data set | Review, report & improve measures | Monitor core data set as business as usual | Clinical manager / Ward / Directorate
FTE calculation | Main steps | Actions | By who
FTE calculation | Set up working group and workshops | Agree working group members & TOR | CCDM council
FTE calculation | Set up working group and workshops | Guide discussion on terms of reference for FTE working group | CCDM Site Coordinator Programme Consultant
FTE calculation | Set up working group and workshops | Present Introduction to FTE calculations (PPP) | CCDM Site Coordinator Programme Consultant
FTE calculation | Set up working group and workshops | Set up regular working group meetings | CCDM Site Coordinator Programme Consultant
FTE calculation | Set up working group and workshops | Maintain patient acuity system data integrity & accuracy | Clinical manager / Ward / Directorate
FTE calculation | Set up working group and workshops | Workshop How to use FTE calculation stocktake | CCDM Site Coordinator Programme Consultant
FTE calculation | Set up working group and workshops | Coordinate information gathering of the stocktake | CCDM Site Coordinator Programme Consultant
FTE calculation | Set up working group and workshops | Plan remaining workshops | CCDM Site Coordinator Programme Consultant
FTE calculation | Set up working group and workshops | Present Detailed FTE Calculation (PPP) | Programme Consultant
FTE calculation | Set up working group and workshops | Attend workshops on FTE calculation detailed information | Working group / CCDM council
FTE calculation | Complete stockstake & agree detailed workplan | Guide discussion on stocktake findings & implementation options | CCDM Site Coordinator Programme Consultant
FTE calculation | Complete stockstake & agree detailed workplan | Review stocktake findings & agree options for implementation | Working group
FTE calculation | Complete stockstake & agree detailed workplan | Endorse & communicate sequence for implementation | CCDM council
FTE calculation | Complete stockstake & agree detailed workplan | Draft detailed workplan | CCDM Site Coordinator Programme Consultant
FTE calculation | Complete stockstake & agree detailed workplan | Agree detailed workplan & report | Working group
FTE calculation | Complete stockstake & agree detailed workplan | Monitor progress | CCDM council
FTE calculation | Collect, collate & agree the data inputs | Guide discussion on agreeing the assumptions & calculations | CCDM Site Coordinator Programme Consultant
FTE calculation | Collect, collate & agree the data inputs | Agree assumptions & calculations | Working group
FTE calculation | Collect, collate & agree the data inputs | Endorse assumptions & standard operating procedures | CCDM council
FTE calculation | Collect, collate & agree the data inputs | Authorise software access for DHB administrator & others as needed | CCDM council
FTE calculation | Collect, collate & agree the data inputs | Provide current roster & budget information | Clinical manager / Ward / Directorate
FTE calculation | Collect, collate & agree the data inputs | Workshop How to navigate the FTE calculation data request schedule | CCDM Site Coordinator Programme Consultant
FTE calculation | Collect, collate & agree the data inputs | Collect & collate data inputs | CCDM Site Coordinator Programme Consultant
FTE calculation | Collect, collate & agree the data inputs | Guide discussion on agreeing the data entry into the software | CCDM Site Coordinator Programme Consultant
FTE calculation | Collect, collate & agree the data inputs | Workshop software demonstration of features & functionality | CCDM Site Coordinator Programme Consultant
FTE calculation | Collect, collate & agree the data inputs | Agree the data inputs | Working group
FTE calculation | Enter data into software & complete roster testing | Workshop How to enter the data into the software | CCDM Site Coordinator Programme Consultant
FTE calculation | Enter data into software & complete roster testing | Enter data into software | CCDM Site Coordinator
FTE calculation | Enter data into software & complete roster testing | Guide discussion on How to use the FTE calculation checklist | CCDM Site Coordinator Programme Consultant
FTE calculation | Enter data into software & complete roster testing | Compile FTE calculation checklist | CCDM Site Coordinator Programme Consultant
FTE calculation | Enter data into software & complete roster testing | Share study/s | CCDM Site Coordinator
FTE calculation | Enter data into software & complete roster testing | Workshop How to do roster testing | Programme Consultant
FTE calculation | Enter data into software & complete roster testing | Complete roster testing. Select recommended roster | Programme Consultant
FTE calculation | Enter data into software & complete roster testing | Agree recommended roster | Working group
FTE calculation | Enter data into software & complete roster testing | Discuss 'what if charts' and opportunities for staff mix changes/swing shifts | Working group
FTE calculation | Enter data into software & complete roster testing | Workshop Interpreting the multiward report from the software | Programme Consultant
FTE calculation | Enter data into software & complete roster testing | Workshop Interpreting the results of the FTE calculation checklist | Programme Consultant
FTE calculation | Enter data into software & complete roster testing | Present Translating the FTE into practice (PPP) | Programme Consultant
FTE calculation | Enter data into software & complete roster testing | Review checklist (+/- multiward report) | Working group
FTE calculation | Draft report & agree recommendations | Draft a progress update to staff | Working group
FTE calculation | Draft report & agree recommendations | Endorse & distribute update to staff | CCDM council
FTE calculation | Draft report & agree recommendations | Draft FTE calculation report/s | CCDM Site Coordinator Programme Consultant
FTE calculation | Draft report & agree recommendations | Finalise report & present to Council | Working group
FTE calculation | Draft report & agree recommendations | Draft decision document | Working group
FTE calculation | Draft report & agree recommendations | Endorse decisions & send to ELT/Board for sign off | CCDM council
FTE calculation | Draft report & agree recommendations | Finalise decision document | CCDM council
FTE calculation | Draft report & agree recommendations | Communicate final decision to staff | CCDM council
FTE calculation | Implement FTE & roster, monitor outcomes | Authorise implementation of changes, if any | CCDM council
FTE calculation | Implement FTE & roster, monitor outcomes | Roster as per new roster model from advised start date | Clinical manager
FTE calculation | Implement FTE & roster, monitor outcomes | Monitor core data set as business as usual. Repeat FTE calculation annually | CCDM council
FTE calculation | Implement FTE & roster, monitor outcomes | Monitor core data set as business as usual | Clinical manager / Ward / Directorate
Variance response management | Main steps | Actions | By who
Variance response management | Step up working group & workshops | Agree working group members & terms of reference | CCDM council
Variance response management | Step up working group & workshops | Guide discussion on working group TOR | CCDM Site Coordinator Programme Consultant
Variance response management | Step up working group & workshops | Set up regular working group meetings | CCDM Site Coordinator Programme Consultant
Variance response management | Step up working group & workshops | Guide discussion on workshops outline | CCDM Site Coordinator Programme Consultant
Variance response management | Step up working group & workshops | Plan the workshops | CCDM Site Coordinator Programme Consultant
Variance response management | Step up working group & workshops | Present variance response management - an introduction | CCDM Site Coordinator Programme Consultant
Variance response management | Step up working group & workshops | Guide discussion on variance response management stocktake | CCDM Site Coordinator Programme Consultant
Variance response management | Step up working group & workshops | Guide discussion on detailed workplan | CCDM Site Coordinator Programme Consultant
Variance response management | Complete stocktake & agree roll out plan | Initiate stocktake | Working group
Variance response management | Complete stocktake & agree roll out plan | Coordinate information gathering for the stocktake | CCDM Site Coordinator Programme Consultant
Variance response management | Complete stocktake & agree roll out plan | Review stocktake findings | Working group
Variance response management | Complete stocktake & agree roll out plan | Agree strategy for overall roll out (by ward, by directorate, whole of hospital) | Working group
Variance response management | Complete stocktake & agree roll out plan | Endorse strategy for overall roll out | CCDM council
Variance response management | Complete stocktake & agree roll out plan | Localise & distribute VRM is about & VRM learn today | CCDM Site Coordinator Programme Consultant
Variance response management | Write business case & set up the workstreams | Draft business case for integrated operating centres | Working group
Variance response management | Write business case & set up the workstreams | Draft business case for capacity at a glance screens | Working group
Variance response management | Write business case & set up the workstreams | Endorse business case | CCDM council
Variance response management | Write business case & set up the workstreams | Appoint the integrated operations centre manager | CCDM council
Variance response management | Write business case & set up the workstreams | Establish regular meetings for each workstream | CCDM council
Variance response management | Write business case & set up the workstreams | Guide the discussion on specification for the integrated operations centre | CCDM Site Coordinator Programme Consultant
Variance response management | Write business case & set up the workstreams | Develop workplan for integrated operations centres | Working group
Variance response management | Write business case & set up the workstreams | Guide the discussion on specifications for capacity at a glance screens | CCDM Site Coordinator Programme Consultant
Variance response management | Write business case & set up the workstreams | Develop workplan for capacity at a glance screens | Working group
Variance response management | Write business case & set up the workstreams | Guide the discussion on staff reallocation guidelines & feedback | CCDM Site Coordinator Programme Consultant
Variance response management | Write business case & set up the workstreams | Guide discussion on care capacity meetings standard operating procedure | CCDM Site Coordinator Programme Consultant
Variance response management | Write business case & set up the workstreams | Guide discussion on variance indicator score & standard operating procedure | CCDM Site Coordinator Programme Consultant
Variance response management | Write business case & set up the workstreams | Develop workplan for variance indicator score | Working group
Variance response management | Agree detailed workplan, specifications & standard operating procedures | Agree detailed workplans | Working group
Variance response management | Agree detailed workplan, specifications & standard operating procedures | Endorse & communicate detailed workplans | CCDM council
Variance response management | Agree detailed workplan, specifications & standard operating procedures | Update the variance response management is about & distribute | CCDM Site Coordinator Programme Consultant
Variance response management | Agree detailed workplan, specifications & standard operating procedures | Design/revise integrated operation centre space | Working group
Variance response management | Agree detailed workplan, specifications & standard operating procedures | Draft & agree specification and interface requirements for capacity at a glance screens (including variance indicator score) | Working group
Variance response management | Agree detailed workplan, specifications & standard operating procedures | Draft & agree standard operating procedures | Working group
Variance response management | Agree detailed workplan, specifications & standard operating procedures | Roll out variance indicator score and standard operating procedures | Working group
Variance response management | Agree detailed workplan, specifications & standard operating procedures | Update the variance response management is about & distribute | CCDM Site Coordinator Programme Consultant
Variance response management | Implement the tools and monitor outcomes | Present variance response management - ward introduction | CCDM Site Coordinator Programme Consultant
Variance response management | Implement the tools and monitor outcomes | Use variance indicator score & standard operating procedures | Clinical manager / Ward / Directorate
Variance response management | Implement the tools and monitor outcomes | Monitor core data set | Clinical manager / Ward / Directorate
Variance response management | Implement the tools and monitor outcomes | Complete monthly reporting | Clinical manager / Ward / Directorate
Variance response management | Implement the tools and monitor outcomes | Monitor progress against progress against workplan | CCDM council
Variance response management | Implement the tools and monitor outcomes | Monitor core data set monthly | CCDM council
Note on C16: Colette Breton: Includes actions from roadmap & workshops
Note on D16: Colette Breton: Who is doing the action

## 4. Monthly status report
What | This worksheet is a template for documenting the monthly status report for the CCDM council.
The status report is taken from the detailed workplan/s.
Who | The CCDM Site Coordinator completes status report in collaboration with the SSHW Programme Consultant.
How | Fill in the blanks below and/or overtype each month.
Copy and paste actions from the detailed workplan from that month into the completed column.
Copy and paste items from the detailed workplan for the following month into the planned column.
Complete the traffic light for scope, schedule and risks. Colour boxes as appropriate.
Exception report on risks and issues at the bottom of the page.
Hide - what, who, how, when rows. PDF the status report and save with month and year in the file name.
Distribute the status report with the monthly CCDM council agenda.
When | Complete every month for the previous month.
Date: | Completed by: | Status:
Component | Completed | Planned | Comments
CCDM governance
CCDM governance
CCDM governance
Patient acuity
Patient acuity
Patient acuity
Core data set
Core data set
Core data set
FTE calculation
FTE calculation
FTE calculation
Variance resonse management
Variance resonse management
Variance resonse management
Risks/Issues:
Scope
Schedule
Risks
CCDM monthly status report

## 5. Quarterly report
[12 empty] | Ahead of schedule | No action required-FYI
[12 empty] | On schedule | Ongoing
[12 empty] | Over 30 days behind schedule | Closed
Over 60 days behind schedule
XXX DHB CCDM FY 17-18 Workplan - Issues register
[5 empty] | No. | Date Raised | Description | Impact on CCDM | Mitigation Owner | Mitigation Strategy | Current Status
1
2
3
4
5
Standard | No. | Activities for FY 17-18 | Timelines | Variance to plan | 6
1 Governance | 1 |  |  | On schedule
| 2 |  |  | On schedule
| 3 |  |  | On schedule
| 4 |  |  | On schedule
2 Patient acuity | 5 |  |  | On schedule
| 6 |  |  | On schedule
| 7 |  |  | On schedule
3 Core data set | 8 |  |  | On schedule
4 Staffing methodology | 9 |  |  | On schedule
| 10 |  |  | On schedule
| 11 |  |  | On schedule
| 12 |  |  | On schedule
5. Variance response management | 13 |  |  | On schedule
| 14 |  |  | On schedule
| 15 |  |  | On schedule
| 16 |  |  | On schedule
| 17 |  |  | On schedule
Work plan - High level status reporting Q1
Overview
DHB Name:
Date commenced CCDM:
FTE resource:
TrendCare version:
Date endorsed by CCDM Council:
Risks/variance to plan
Other comments
Quarter X
XXXX DHB CCDM Work plan report for 2017-2018B
DHB LOGO
Work plan - High level status reporting Q1
Overview
DHB Name:
Date commenced CCDM:
FTE resource:
TrendCare version:
Date endorsed by CCDM Council:
Risks/variance to plan
Next steps/Pending decisions
Recent updates
Other comments
Quarter X
XXXX DHB CCDM Work plan reportB
DHB LOGO